## Executive Summary
TrustIssue — Complete Feature & Reliability Audit
Source audit date: 2026-07-23 ¦ Scope: Flutter UI + native Android child app ¦ IMPORTANT: no compile or runtime test was run.
Outcome | Value | Meaning | Reliability scale | Meaning
Total feature entries | 74 | Includes implemented, limited, coming-soon, removed, and legacy items. | 5 | Strong deterministic source design; normal device validation still required.
Implemented — runtime pending | 53 | Source paths exist; must still compile and run on devices. | 4 | Strong design with lifecycle/OEM edge cases to prove.
Implemented with platform limits | 13 | Android/OEM behavior prevents a 100% guarantee. | 3 | Useful but inherently platform/OEM/network limited.
UI-only — Coming soon | 2 | Visible but deliberately disabled; not working protection. | 2 | Legacy/prototype/partial.
Removed by decision | 5 | Intentionally absent from current product. | 1 | UI-only; no working enforcement.
Legacy/unreferenced | 1 | Cleanup candidate, not part of the active user flow.
P0 release checks | 24 | Must pass before calling protection reliable.
Average expected reliability | 3.81 | Design estimate only; not a measured test result.
Runtime tests completed | 0 | User instructed not to compile; every checklist item remains NOT RUN.
Bottom line
• Accessibility is optional for all currently implemented core Focus modes. When it is healthy, it becomes the fast package-event engine; otherwise Usage Access + Overlay remains the compatible engine.
• Core blocking is not a force-stop. TrustIssue launches its own opaque gate Activity/task above the target app; the target normally remains in memory/background.
• The compatible engine is valuable but cannot be guaranteed equally on every Android/OEM because UsageStats timing, background Activity starts, overlays, and battery killers vary.
• Strict = maximum 8 hours + DND + protected emergency exit. Locked Strict = Timer only, maximum 3 hours, DND, no emergency exit.
• The local VPN is DNS/hostname protection for allowed browsers only. It does not decrypt web pages, but it cannot promise to stop every unknown encrypted-DNS/proxy bypass.
• Before release, the P0 test matrix and Google Play policy review are mandatory. The workbook does not claim any feature is runtime-verified.
Status | Count
Implemented — runtime validation pending | 53
Implemented with platform limits | 13
UI-only — Coming soon | 2
Removed by product decision | 5
Legacy/unreferenced — cleanup pending | 1

## Feature Inventory
Feature Inventory
Filter by Area, status, reliability, priority, permission, or Accessibility role. Reliability is a source-design estimate, not measured evidence.
ID | Area | Feature | Implementation status | What the user sees / what it does | How it works internally | Permissions / access | Accessibility role | Expected reliability (1-5) | Known limitations / risks | How to verify / accept | Primary source files | Release priority | Runtime validation | Pending action
F-001 | Onboarding | Permission-free onboarding | Implemented — runtime validation pending | Introduces Focus without forcing permission screens during first launch. | The Flutter onboarding screen contains no permission requests; access is requested only when a dependent feature is started. | None | Not required | 5 | A future onboarding edit could accidentally add eager permission calls. | Fresh-install test: complete onboarding and confirm Android shows no Usage, Overlay, Accessibility, VPN, DND, notification, or battery prompt. | lib/screens/onboarding_screen.dart; lib/screens/home_shell.dart | P1 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-002 | Onboarding | Default PDF reader choice | Implemented — runtime validation pending | Lets the user choose a PDF reader for study handoffs. | Native package discovery finds eligible PDF handlers; the selected package is persisted locally and checked before App Study starts. | Package visibility queries only | Not required for selection; automatic cross-app recognition is more reliable with Accessibility | 4 | If the selected reader is uninstalled or becomes a browser, the user must choose again. | Install two PDF readers; choose one; restart app; start App Study; uninstall it and confirm a new selection is requested. | lib/screens/onboarding_screen.dart; lib/screens/settings_screen.dart; android/.../StudyToolResolver.kt; android/.../MainActivity.kt | P1 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-003 | Navigation & UI | Four-tab navigation | Implemented — runtime validation pending | Provides Focus, Blocks, Reports, and Settings tabs. | Flutter HomeShell swaps four embedded screens and refreshes usage or analytics when relevant tabs open. | None | Not required | 5 | Small-screen and large-font layouts still need device checks. | Open every tab repeatedly during idle and active Focus; verify state is preserved and there is no clipped navigation at 1.0x–2.0x font scale. | lib/screens/home_shell.dart | P1 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-004 | Focus UI | Focus home dashboard | Implemented — runtime validation pending | Shows usage time, focus time, selected apps, current mode, and a central start/edit control. | Flutter combines locally stored configuration with native session state, break state, usage summary, and app icons. | Usage Access is needed for real usage totals; UI itself needs none | Not required | 4 | Usage totals show zero until Usage Access is granted; icon loading is asynchronous. | Compare home totals with Android Digital Wellbeing for the same day; verify active session timer updates every second. | lib/screens/focus_home_screen.dart; lib/screens/home_shell.dart; lib/services/native_bridge.dart | P1 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-005 | Focus UI | Circular start/edit interaction | Implemented — runtime validation pending | Tapping the circle or Edit opens a compact Focus setup sheet; active Focus shows live state. | Flutter modal sheet edits an in-memory StudySettings copy and persists only confirmed values. | None | Not required | 5 | Gesture and sheet-height behavior needs testing on small devices. | Tap circle and Edit; change values; cancel and confirm; verify cancel does not persist and confirm does. | lib/screens/focus_home_screen.dart | P1 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-006 | Session type | Timer session | Implemented — runtime validation pending | Counts down for a selected fixed duration. | Duration is capped by protection mode, persisted in Flutter preferences, mirrored into native state, and guarded by an Android timeout alarm. | Usage Access + Display over apps when starting Focus; notification prompt is optional | Optional performance enhancement | 4 | AlarmManager setAndAllowWhileIdle is not exact; the foreground observer also performs completion checks. | Run 1-, 5-, and 30-minute timers with screen on/off; confirm end occurs once and protection is removed. | lib/screens/focus_home_screen.dart; lib/services/settings_store.dart; android/.../TrackerConfig.kt; android/.../FocusSessionTimeoutReceiver.kt | P1 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-007 | Session type | Duration wheel | Implemented — runtime validation pending | Allows hours/minutes selection within the selected mode's safety maximum. | Flutter wheel clamps Normal to 24h, Strict to 8h, and Locked Strict to 3h. | None | Not required | 5 | Boundary values still require UI and persistence tests. | Test 0, 1 minute, mode maximum, and one step beyond maximum; verify invalid values cannot start. | lib/screens/focus_home_screen.dart; lib/services/settings_store.dart | P1 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-008 | Session type | Stopwatch session | Implemented — runtime validation pending | Counts focused time upward until the user exits; earned breaks appear as focus time accumulates. | Native state stores Stopwatch mode, uses elapsedRealtime for active spans, and applies a safety deadline. Locked Strict is automatically disabled. | Same as Focus start; DND additionally for Strict Stopwatch | Optional performance enhancement | 4 | Stopwatch is intentionally not available with Locked Strict; long-duration safety deadline must be tested. | Run Normal and Strict Stopwatch; background/reopen app; reboot test; confirm count does not double and exit rules are correct. | lib/screens/focus_home_screen.dart; lib/services/settings_store.dart; android/.../TrackerConfig.kt | P1 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-009 | Session type | Pomodoro | Removed by product decision | No Pomodoro tab or configuration is presented. | Product decision: Timer and Stopwatch remain; automatic breaks replace a separate Pomodoro mode. | None | Not applicable |  | Old design screenshots may still create expectation. | Search UI and source references; confirm no active Pomodoro navigation or start path exists. | lib/screens/focus_home_screen.dart | N/A | NOT RUN — user requested no compilation | Keep removed unless product direction changes.
F-010 | Tracking | Continuous timer (Book Study) | Implemented — runtime validation pending | Focus time continues against a wall-clock session even when no selected study app is open, except during breaks. | Native Book Study computes focused time from the session clock and pushes the deadline out by permitted break time. | Focus permissions | Optional performance enhancement | 4 | Wall-clock recovery after reboot depends on persisted anchors; clock-change receiver must be tested. | Start 10-minute Continuous timer; use launcher/allowed apps; take break; verify focus and end time calculations. | lib/screens/focus_home_screen.dart; android/.../TrackerConfig.kt | P1 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-011 | Tracking | Selected apps only (App Study) | Implemented — runtime validation pending | Counts focus only while a selected study app or approved study tool is in use. | Allowlist policy resumes and pauses native timing according to observed foreground package transitions. | Usage Access + Display over apps | Optional but materially improves transition speed and PDF/Gallery handoffs | 3 | UsageStats polling can miss very short transitions; PDF/Gallery intent origin cannot always be inferred without Accessibility. | Switch among selected app, launcher, unselected app, PDF, and Gallery; compare elapsed focus with a stopwatch. | lib/screens/focus_home_screen.dart; android/.../TrackerConfig.kt; android/.../SelfControlAccessibilityService.kt; android/.../FocusUsageMonitorService.kt | P1 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-012 | App policy | Block selected apps (blocklist) | Implemented — runtime validation pending | Only chosen distracting apps are blocked during Focus; other non-safety apps remain usable. | FocusPolicyEngine returns a block decision when the foreground package is in the persisted blocked set. | Usage Access + Display over apps | Optional speed enhancement | 4 | Foreground detection and background-start restrictions vary by Android/OEM. | Select three apps; start Focus; test selected, unselected, safety, browser, and TrustIssue packages. | lib/screens/select_apps_screen.dart; android/.../FocusPolicyEngine.kt; android/.../TrackerConfig.kt | P1 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-013 | App policy | Allow only selected apps (allowlist) | Implemented — runtime validation pending | Selected study apps and safety apps are usable; other apps are blocked. | FocusPolicyEngine permits packages in the allowlist plus safety/system exceptions. | Usage Access + Display over apps; VPN consent if an allowed browser exists | Optional speed enhancement | 4 | System helper classification and OEM packages require broad device testing. | Allow one study app; test all other launcher apps, Settings, Phone, Messages, Maps, keyboard, file picker, PDF, and browser. | lib/screens/select_apps_screen.dart; android/.../FocusPolicyEngine.kt; android/.../StudyToolResolver.kt | P1 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-014 | App selection | Installed app discovery | Implemented — runtime validation pending | Lists launchable installed apps, excluding TrustIssue itself. | Native PackageManager queries launcher activities, de-duplicates package names, and sorts by label. | Package visibility query declarations | Not required | 4 | Work-profile, Secure Folder, hidden, instant, or non-launcher components may not appear. | Compare picker against launcher across Samsung/Xiaomi/Pixel and work-profile devices. | android/.../MainActivity.kt; android/app/src/main/AndroidManifest.xml | P1 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-015 | App selection | Search, categories, select-all, and icons | Implemented — runtime validation pending | Searches by app name/package, surfaces known categories first, supports bulk selection, and shows app icons. | Flutter filters/sorts native app metadata; AppIconCache requests PNG icons over MethodChannel and caches them. | None beyond app discovery | Not required | 4 | Category map is curated and incomplete; large app inventories may need performance profiling. | Test 300+ installed apps, rapid search, select-all on filtered results, icon cache after scroll/reopen. | lib/screens/select_apps_screen.dart; lib/services/app_icon_cache.dart; lib/widgets/app_icon_tile.dart | P1 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-016 | Safety | Always-allowed safety apps | Implemented — runtime validation pending | Phone, messages, settings, maps and essential system helpers stay reachable and appear read-only in selection. | Native alwaysAllowedPackages and system/transient-window rules override normal block decisions. | None | Not required | 4 | OEM package names differ; package list needs device-matrix validation and must not over-allow a distracting app. | During allowlist Focus test calls, SMS, Settings, emergency dialer, maps, keyboard, permission controller, chooser, and file picker. | android/.../MainActivity.kt; android/.../FocusForegroundEventPolicy.kt; lib/screens/select_apps_screen.dart | P1 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-017 | Protection mode | Normal Focus | Implemented — runtime validation pending | Up to 24 hours; user can end at any time after confirmation. | Native observer enforces the selected app policy; Flutter stop flow calls native deactivation and preserves completed local metrics. | Usage Access + Display over apps; notification optional; VPN only if browser allowed | Optional speed enhancement | 4 | Compatible mode depends on foreground service survival and OEM battery policy. | Start/end/restart sessions; revoke notification permission; lock screen; verify blocked apps and cleanup. | lib/screens/home_shell.dart; android/.../TrackerConfig.kt; android/.../FocusUsageMonitorService.kt | P1 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-018 | Protection mode | Strict Focus | Implemented — runtime validation pending | Up to 8 hours; enables DND and uses a protected emergency-exit process. | The same blocking engine runs with strict flags; StrictFocusDndController applies alarms-only DND and FocusGateActivity owns emergency exit. | Usage Access + Display over apps + DND policy access; notification optional; VPN conditionally | Optional speed enhancement | 4 | DND behavior and visual suppression vary by Android/OEM; emergency calls must remain possible. | Test 1-minute and maximum-boundary Strict sessions, incoming call/SMS/app notifications, DND restore, and emergency exit. | lib/screens/strict_preparation_screen.dart; android/.../StrictFocusDndController.kt; android/.../FocusGateActivity.kt | P1 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-019 | Protection mode | Locked Strict Focus | Implemented — runtime validation pending | Fixed Timer only, maximum 3 hours, DND active, and no emergency exit or early-stop control. | Locked flag is persisted; native stop API and gate UI reject exit while the session is active; timeout completes it. | Usage Access + Display over apps + DND; VPN conditionally | Optional speed enhancement | 4 | Any bug in timeout/restoration has high user impact; power-cycle and clock-change tests are mandatory before release. | Verify Stopwatch toggle disables Locked; try all UI/native exit paths; reboot/update/change time; confirm automatic end and DND release. | lib/services/settings_store.dart; lib/screens/home_shell.dart; android/.../MainActivity.kt; android/.../TrackerConfig.kt | P0 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-020 | Protection mode | Strict preparation countdown | Implemented — runtime validation pending | Shows a 60-second preparation screen with wait, skip, or cancel before Strict starts. | Flutter full-screen countdown returns a boolean; native activation happens only after confirmation. | None beyond permissions already checked | Not required | 5 | App lifecycle interruption during the preparation screen needs testing. | Wait, skip, cancel, background, rotate, and kill during preparation; confirm Focus starts only after explicit completion. | lib/screens/strict_preparation_screen.dart; lib/screens/home_shell.dart | P1 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-021 | Strict exit | Protected emergency exit | Implemented — runtime validation pending | Strict requires a 60-second wait and at least 10 words; cancel returns to Focus. | Native FocusGateActivity validates word count and countdown, records attempt/cancel/success metrics, then deactivates Strict. | None additional | Not required | 4 | Typed reason is described as local report data; privacy and deletion behavior must match this promise. | Attempt with 0/9/10 words; background/rotate; cancel; complete; verify DND and protection cleanup plus analytics. | android/.../FocusGateActivity.kt; android/.../TrackerConfig.kt | P0 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-022 | Strict exit | Locked Strict has no emergency exit | Implemented — runtime validation pending | No exit button is rendered, and API attempts return a Locked Strict message. | Both Flutter and native layers check the locked flag; timeout is the intended completion route. | None additional | Not required | 4 | Must verify notification actions, recents, deep links, process restart, and settings changes cannot bypass it. | Enumerate every stop path and attempt during active Locked Strict; verify all fail except natural timeout. | lib/screens/home_shell.dart; android/.../MainActivity.kt; android/.../FocusGateActivity.kt; android/.../FocusPillController.kt | P0 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-023 | Notifications | Strict-mode notification blocking via DND | Implemented — runtime validation pending | Strict and Locked Strict use alarms-only DND; Normal Focus does not block notifications. | App-owned DND state is applied, previous user filter/policy is saved, and only app-owned state is released. | DND policy access | Not required | 4 | Calls, alarms, OEM overlays, companion devices, and target-35 DND rule behavior differ; user can revoke access mid-session. | Test incoming calls, emergency call path, SMS, heads-up, lock-screen notifications, alarms, and restore of pre-existing DND. | android/.../StrictFocusDndController.kt; lib/screens/home_shell.dart | P0 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-024 | Breaks | Automatic break earning | Implemented — runtime validation pending | Timer earns one break per 30 configured minutes; Stopwatch earns breaks from completed focused time. | Native TrackerConfig calculates allowed/used break budget and exposes the next available break duration. | Focus permissions | Not required for calculation; observer is needed for enforcement | 4 | Boundary timing and interrupted sessions need tests; UI wording must explain the rule. | Test 29:59, 30:00, 59:59, 60:00, Stopwatch pause/resume, and app restarts. | lib/services/settings_store.dart; android/.../TrackerConfig.kt | P1 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-025 | Breaks | Break app picker | Implemented — runtime validation pending | Lets the user select up to three apps for a temporary break. | FocusGateActivity presents eligible app options and persists the selected break package(s) with a timeout. | Display over apps; foreground observer | Optional speed enhancement | 4 | The user-facing copy says up to three; all multi-selection persistence/enforcement combinations need runtime confirmation. | Select 0/1/3/4 apps; start break; verify only selected apps and safety apps open. | android/.../FocusGateActivity.kt; android/.../TrackerConfig.kt | P1 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-026 | Breaks | Five-minute break slices and early return | Implemented — runtime validation pending | Break time is temporary; ending early returns unused time and restores Focus rules. | Elapsed and wall-clock anchors track actual/allotted/unused break time; manual end and alarm expiry use one cleanup path. | None additional | Optional speed enhancement | 4 | Doze can delay an inexact alarm, so foreground reconciliation must catch expiry immediately on next observation. | End at 30s and let full break expire with screen on/off; verify remaining budget, app blocking, timer, and reports. | android/.../TrackerConfig.kt; android/.../FocusBreakTimeoutReceiver.kt; android/.../FocusGateActivity.kt | P1 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-027 | Floating controls | Floating Focus pill | Implemented — runtime validation pending | Shows a draggable live timer over the active study/break app; expands to break, exit, and collapse controls. | Overlay WindowManager view persists position; visibility policy hides it outside the relevant scope and auto-collapses expanded controls. | Display over apps | Works in both engines | 4 | OEM overlay restrictions, orientation, cutouts, multi-window, and accidental obstruction need testing. | Drag to all edges, rotate, collapse/expand, long-press actions, change apps, lock screen, and restart service. | android/.../FocusPillController.kt; android/.../FocusPillVisibilityPolicy.kt | P1 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-028 | Blocking engine | Usage Access compatible observer | Implemented with platform limits | Provides app blocking without Accessibility by detecting foreground package changes and opening the block gate. | A foreground service polls UsageStats roughly every 300ms while active and slows when idle; overlay safety UI appears before the richer Activity. | Usage Access + Display over apps; notification optional | This is the fallback when Accessibility is off/unhealthy | 3 | UsageStats is delayed/coalesced on some OEMs; brief flashes, background start restrictions, and higher battery use are possible. | Measure 100 blocked launches across Pixel/Samsung/Xiaomi/Oppo/Vivo, screen states, battery modes, rapid switching, split screen, and recents. | android/.../FocusUsageMonitorService.kt; android/.../UsageStatsReader.kt; android/.../FocusBlockOverlayController.kt | P0 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-029 | Blocking engine | Optional Accessibility fast observer | Implemented with platform limits | When manually enabled, blocked app transitions are noticed faster and the same Focus gate is opened. | Accessibility service subscribes only to TYPE_WINDOW_STATE_CHANGED and uses package names; it does not retrieve node text. | Optional Accessibility service access | Primary observer only while the service heartbeat is healthy | 4 | Some payment/banking apps refuse to run while any Accessibility service is enabled; Google Play policy/disclosure compliance is required. | Enable service; verify package-only events and block latency; test payment/banking apps; revoke/kill service mid-session. | android/.../SelfControlAccessibilityService.kt; android/res/xml/self_control_accessibility_service.xml; android/.../ProtectionAccess.kt | P0 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-030 | Blocking engine | Accessibility heartbeat and automatic fallback | Implemented — runtime validation pending | If Accessibility is enabled but not actually running, compatible protection resumes automatically. | Accessibility emits an in-process heartbeat every 3s; compatible service owns Focus unless the heartbeat is fresh (maximum age 10s). Daily limits remain monitored. | No new permission | Defines engine ownership | 4 | In-process heartbeat resets after process death; overlap/thrash during service reconnect must be stress-tested. | During Focus kill/restart Accessibility service, toggle it in Settings, and kill the app process; confirm one gate and no unprotected gap. | android/.../ProtectionAccess.kt; android/.../SelfControlAccessibilityService.kt; android/.../FocusUsageMonitorService.kt | P0 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-031 | Blocking UI | Immediate safety overlay | Implemented with platform limits | A minimal opaque block surface appears immediately while the full Focus gate Activity starts. | FocusBlockOverlayController uses SYSTEM_ALERT_WINDOW from the compatible observer and is hidden only after the gate broadcasts visible state. | Display over apps | Not dependent | 4 | Overlay may be blocked by secure/system windows; it must never remain stuck above allowed apps. | Launch blocked apps 100 times; slow device with animation scale; rotate; lock/unlock; crash gate; verify no flash and no stuck overlay. | android/.../FocusBlockOverlayController.kt; android/.../FocusUsageMonitorService.kt; android/.../FocusGateActivity.kt | P0 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-032 | Blocking UI | Full-screen Focus gate | Implemented — runtime validation pending | Shows app icon, blocked reason, live timer/status, break control, and only the exit action allowed by the mode. | A native singleTask Activity is launched above the blocked app; it appears as a TrustIssue task/card and finishes when Focus is no longer applicable. | Display over apps is used by protection; Activity itself needs none | Same UI for both engines | 4 | It does not force-stop the target app; the app remains in memory/background. Recents behavior and OEM activity launch rules vary. | Test block gate from launcher, recents, notification deep link, PiP, split screen, and repeated taps; inspect recents card and back behavior. | android/.../FocusGateActivity.kt; android/app/src/main/AndroidManifest.xml | P0 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-033 | Blocking UI | Gate-closing animation | Implemented — runtime validation pending | Block screen enters with two panels closing and a short fade/scale so the transition feels like a gate rather than a sudden popup. | Native view animations run for about 180–190ms before settling into the blocking content. | None | Not dependent | 4 | Animation scale settings, low-end devices, and repeated Activity reuse may produce jank. | Record 60fps/120fps screen video on low/mid/high devices with animator scale 0x/0.5x/1x/2x. | android/.../FocusGateActivity.kt; android/.../FocusBlockOverlayController.kt | P1 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-034 | Media | Blocked-app audio containment | Implemented with platform limits | Opaque gate/background transition should naturally pause foreground video/audio; if audio remains active, TrustIssue briefly takes audio focus. | After a 350ms settle delay, BlockedMediaController requests transient audio focus only when Android reports active music, then releases it after 850ms. | No special permission | Works in both engines | 3 | Android cannot identify which app owns global active audio here; unrelated Spotify/music may briefly duck/pause, but no global media-key is sent. | Test YouTube/Instagram/VLC audio plus Spotify playing separately; verify blocked media stops and unrelated music resumes automatically. | android/.../BlockedMediaController.kt; android/.../SelfControlAccessibilityService.kt; android/.../FocusUsageMonitorService.kt | P0 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-035 | Daily limits | Per-app daily limits | Implemented — runtime validation pending | Lets the user set 15–240 minute presets (or persisted values up to 24h); blocked app receives a daily-limit gate after usage is exhausted. | UsageStatsReader aggregates today's package use; the all-day compatible foreground service compares totals with persisted limits. | Usage Access + Display over apps; notification optional | Not required; compatible monitor continues even when Accessibility handles Focus | 3 | UsageStats accuracy and midnight/session boundaries vary; service survival depends on OEM battery policy. | Set short test limits; cross midnight; change time zone; reboot; use app in split screen/PiP; compare Android usage totals. | lib/screens/blocks_screen.dart; lib/screens/home_shell.dart; android/.../UsageStatsReader.kt; android/.../FocusUsageMonitorService.kt | P0 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-036 | Daily limits | Daily limit add/edit/remove and progress | Implemented — runtime validation pending | Blocks tab shows configured apps, used/limit progress, and add/edit/remove controls. | Flutter loads today's native usage summary and updates a locally persisted package-to-minutes map; native protection is resynchronised. | Usage Access for real progress; Overlay to enforce | Not required | 4 | UI can show a saved-but-not-active limit if required access is denied; the message must remain obvious. | Add, edit, remove, deny permissions, reopen app, and verify UI accurately distinguishes saved versus active. | lib/screens/blocks_screen.dart; lib/screens/home_shell.dart; lib/services/settings_store.dart | P1 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-037 | Web protection | Allowed-browser local VPN | Implemented with platform limits | An allowed browser can be used during Focus while adult, bypass, blocked-app, and custom domains are filtered. | Only allowed browser packages are added to a split-tunnel VpnService; their synthetic-DNS traffic is parsed and forwarded over encrypted DNS. | One-time Android VPN consent + Internet/network state; foreground notification | Not required | 3 | DNS filtering cannot inspect page content or paths and cannot guarantee coverage against every in-app encrypted DNS/proxy protocol. | Test Chrome/Brave/Firefox/Samsung Internet across Wi-Fi/mobile, Private DNS, browser Secure DNS, QUIC, VPN conflict, and network switching. | android/.../FocusWebProtectionService.kt; android/.../DnsPacketCodec.kt; android/.../WebProtectionConfig.kt | P0 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-038 | Web protection | Mandatory domain categories | Implemented with platform limits | Blocks bundled adult, proxy, secure-DNS/bypass, and service-domain rules before upstream resolution. | Normalized hostname and subdomain matching returns NXDOMAIN and broadcasts a category for the local explanation screen. | VPN consent when browser allowed | Not required | 3 | Bundled lists are intentionally small and become stale; Cloudflare Family provides broader upstream categorisation but is an external dependency. | Run curated domain fixtures including subdomains, IDN/punycode, trailing dots, uppercase, malformed names, and newly registered bypass sites. | android/.../WebProtectionConfig.kt; android/.../FocusWebProtectionService.kt | P0 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-039 | Web protection | Blocked app's web version | Implemented with platform limits | When a known service app is blocked, matching web domains are also blocked in an allowed browser. | WebProtectionConfig maps selected package rules to curated service-domain sets and labels the block as app + web rule. | VPN consent | Not required | 3 | Only mapped services/domains are covered; mirrors, alternate domains, and web search results can bypass. | For every mapped package, block the app and test canonical, mobile, short-link, alternate, and login domains. | android/.../WebProtectionConfig.kt; android/.../WebBlockActivity.kt | P1 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-040 | Web protection | Custom website rules | Implemented — runtime validation pending | User can add/edit/remove custom domains from app selection or Blocks. | Flutter normalizes and persists a domain set; VPN policy performs exact/subdomain matching. | VPN consent when browser allowed | Not required | 4 | IP addresses, URL paths, search keywords, and domains contacted without DNS are outside scope. | Add valid/invalid domains and subdomains; restart app/session; confirm only matching hostnames are blocked. | lib/screens/select_apps_screen.dart; lib/screens/blocks_screen.dart; android/.../WebProtectionConfig.kt | P1 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-041 | Web protection | Encrypted family DNS and SafeSearch | Implemented with platform limits | Allowed DNS requests go to Cloudflare Family over HTTPS; selected search/video hostnames receive SafeSearch aliases. | HTTPS DNS-message POST, 30-second response cache, and CNAME rewriting are implemented in the VPN service. | Internet + VPN consent | Not required | 3 | External resolver availability/privacy terms, certificate/network failures, captive portals, and service hostname changes affect results. | Validate known adult/malware domains, SafeSearch on supported engines, cache behavior, captive portal, offline/reconnect, and TLS interception. | android/.../FocusWebProtectionService.kt; android/.../DnsPacketCodec.kt | P0 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-042 | Web protection | Fail-closed browser protection | Implemented — runtime validation pending | If VPN permission/start/health fails, allowed browsers are blocked instead of silently becoming unprotected. | Start flow moves browsers into the block policy when consent is declined; running service transitions through starting/active/reconnecting/degraded and the observer checks browser coverage. | Usage/Overlay plus conditional VPN consent | Works with either foreground engine | 4 | A race between browser launch and VPN state must be stress-tested; false fail-closed blocks are safer but frustrating. | Decline/revoke VPN, kill VPN service, remove network, install browser mid-session, and force upstream failure; browser must not open unprotected. | lib/screens/home_shell.dart; android/.../WebProtectionConfig.kt; android/.../FocusWebProtectionService.kt | P0 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-043 | Web protection | Website block explanation screen | Implemented — runtime validation pending | Shows the blocked domain/category and safe-return actions without displaying page content or history. | WebBlockActivity receives only normalized domain and policy category from a local broadcast/intent. | None beyond active VPN | Accessibility may issue Back before opening it; compatible mode opens the same screen | 4 | Browser navigation state differs; returning may re-trigger the same DNS request. | Trigger every category and both unavailable/normal states; test Back, retry, close browser, and repeated redirect loops. | android/.../WebBlockActivity.kt; android/.../FocusWebProtectionService.kt | P1 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-044 | Study tools | PDF/Gallery tool classification | Implemented with platform limits | Recognizes installed PDF readers and gallery/system picker packages as possible study tools. | Native intent queries and curated system package sets classify PDF_READER or GALLERY without reading files. | Package visibility queries | Automatic foreground-origin correlation is more reliable with Accessibility | 3 | OEM gallery/file-manager packages and multi-role apps can be misclassified; a browser PDF handler is excluded from default-reader eligibility. | Test PDF and image flows on Pixel/Samsung/Xiaomi/Oppo/Vivo, Files by Google, Drive, Photos, Gallery, and browser PDF viewers. | android/.../StudyToolResolver.kt; android/app/src/main/AndroidManifest.xml | P1 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-045 | Study tools | Two-minute temporary study-tool access | Implemented with platform limits | A confirmation gate can grant a study tool two minutes once per tool per session, then returns to the source study app. | TrackerConfig records per-session use, schedules a timeout receiver, and FocusPill offers an early return. | Foreground observer + overlay | Transition/source detection is strongest with Accessibility; compatible mode uses UsageStats heuristics | 3 | Without Accessibility, Android cannot always prove whether Gallery/PDF was opened by a study app; confirmation is intentional friction. | Open tool from selected and unrelated apps, use once/twice, expire/background/reboot, and verify return package and timer accounting. | android/.../StudyToolGateActivity.kt; android/.../StudyToolTimeoutReceiver.kt; android/.../TrackerConfig.kt | P0 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-046 | Study tools | Session-long selected PDF access | Implemented with platform limits | The configured default PDF reader can be allowed as a study app for the current Focus session. | StudyToolGate checks selected default reader and session eligibility, then adds a session-scoped grant whose time counts as study. | Foreground observer + overlay | More reliable with Accessibility | 3 | Only the selected PDF reader is eligible; switching handlers mid-session intentionally triggers a gate. | Grant and deny; open same/different reader repeatedly; uninstall/disable reader; confirm grant expires when Focus ends. | android/.../StudyToolGateActivity.kt; android/.../StudyToolResolver.kt; android/.../TrackerConfig.kt | P1 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-047 | Study tools | Gallery remains temporary | Implemented with platform limits | Gallery access is never made session-long; user confirms temporary use. | ToolKind.GALLERY is marked sessionEligible=false, reducing the risk that direct Gallery distraction is counted as study. | Foreground observer + overlay | More reliable with Accessibility | 3 | System photo pickers and galleries may use several packages; false-positive confirmation gates remain possible. | Open Gallery directly versus through selected app/system picker and verify temporary-only UI and timeout. | android/.../StudyToolResolver.kt; android/.../StudyToolGateActivity.kt | P1 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-048 | Reports | Daily/weekly/monthly reports | Implemented — runtime validation pending | Shows a selected day, last 7 days, or last 30 days with focus time, completion, sessions, attempts, and returns. | Flutter aggregates up to 30 locally stored native daily JSON metrics and compares periods. | None | Not required | 4 | No cloud backup; deleted app data removes reports. Aggregation accuracy depends on event recording correctness. | Create controlled sessions/events across dates; independently calculate totals and compare all periods. | lib/screens/analytics_screen.dart; android/.../TrackerConfig.kt; lib/services/native_bridge.dart | P1 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-049 | Reports | Focus trend chart and average | Implemented — runtime validation pending | Displays a bar chart of focus by day and average per day. | Flutter derives chart height and labels from local daily metrics. | None | Not required | 5 | Dense 30-day labels and zero-data layouts need visual testing. | Test 0, 1, 7, and 30 days with extreme values and date selection. | lib/screens/analytics_screen.dart | P1 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-050 | Reports | Distraction attempts and outcomes | Implemented — runtime validation pending | Shows top blocked apps, attempt counts, returned-to-focus outcomes, and ended-focus outcomes. | Both observers and FocusGate record package-level attempts, handled returns, blocked duration, and emergency/normal exits into daily metrics. | None | Not required | 4 | Rapid repeated opens are throttled, so counts represent blocking moments rather than every OS event. | Script known attempts/returns/exits; verify top-five order, totals, percentage, and no double count during gate reuse. | lib/screens/analytics_screen.dart; android/.../TrackerConfig.kt; android/.../FocusGateActivity.kt | P1 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-051 | Reports | Focused time by study app | Implemented — runtime validation pending | Shows where focus happened and duration per selected study app. | Native timing spans are attributed by package and Flutter displays the top entries. | None | Package observation is more precise with Accessibility | 3 | UsageStats polling can undercount short visits; Continuous timer may not attribute all focus to an app. | Use two selected apps for controlled intervals; compare per-app sum with total focus and explain Continuous remainder. | lib/screens/analytics_screen.dart; android/.../TrackerConfig.kt | P1 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-052 | Reports | Break control metrics | Implemented — runtime validation pending | Shows break count, allotted time, actually used time, percentage, and unused time returned. | Native break start/end paths increment daily counts/durations and per-app break metrics. | None | Not required | 4 | Crash/reboot during break must reconcile exactly once. | Take manual and expired breaks, return early, reboot mid-break, and independently sum metrics. | lib/screens/analytics_screen.dart; android/.../TrackerConfig.kt | P1 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-053 | Reports | Motivation/insight cards | Implemented — runtime validation pending | Generates local tips from focus change, completion, returns, and top distraction. | Deterministic Flutter rules choose a badge, title, explanation, and tip from period summaries. | None | Not required | 5 | Insights are heuristic, not clinical or predictive. | Create fixtures for no data, improved focus, high completion, high return, and top distraction branches. | lib/screens/analytics_screen.dart | P1 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-054 | Privacy | Local-only settings and analytics | Implemented — runtime validation pending | No account/cloud sync is required; app rules, timing, attempts, breaks, and reports remain on-device. | SharedPreferences and local JSON metrics store configuration and summaries; manifest disables Android backup. | None | Accessibility metadata is package-only and does not request node content | 4 | VPN necessarily sends allowed-browser DNS queries to Cloudflare Family; this is external network processing, not fully local. | Inspect network traffic outside active VPN and storage/backup behavior; verify no app server endpoints or analytics SDKs. | android/app/src/main/AndroidManifest.xml; android/.../TrackerConfig.kt; lib/services/settings_store.dart; lib/screens/settings_screen.dart | P0 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-055 | Diagnostics | Redacted local debug log | Implemented — runtime validation pending | Records protection lifecycle/health messages for troubleshooting without screen content. | TrustIssueDebugLog writes bounded local diagnostic entries; callers truncate package/domain/error text. | None | Records service lifecycle only | 4 | Package names and blocked domains can still be sensitive metadata and need retention/redaction review. | Exercise features; inspect export for passwords, typed emergency reason, full URLs, messages, notification text, and unbounded growth. | android/.../TrustIssueDebugLog.kt; lib/screens/settings_screen.dart; android/.../MainActivity.kt | P0 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-056 | Diagnostics | Export and clear diagnostics | Implemented — runtime validation pending | Settings can export the local diagnostic log and clear it. | Flutter calls native bridge methods; Android returns a shareable/export payload and clears local log on request. | System share sheet when exporting | Not required | 4 | Destination apps are outside TrustIssue privacy control after the user shares. | Export empty/non-empty/large log; cancel share; clear and re-export; inspect content. | lib/screens/settings_screen.dart; lib/services/native_bridge.dart; android/.../MainActivity.kt | P1 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-057 | Privacy | Clear local reports | Implemented — runtime validation pending | User can delete locally stored report history after confirmation. | Settings invokes native analytics deletion and reloads the Reports state. | None | Not required | 4 | Must verify no orphaned keys, active-session corruption, or stale UI cache. | Create history; clear while idle; reopen/restart; confirm zero data and current configuration remains. | lib/screens/settings_screen.dart; android/.../TrackerConfig.kt; android/.../MainActivity.kt | P1 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-058 | Settings | Permission and protection status | Implemented — runtime validation pending | Shows Usage Access, Overlay, Accessibility, Strict DND, VPN/web status, notification, and optional battery status with contextual actions. | Flutter refreshes native access/state methods on lifecycle resume and opens the correct Android settings screen. | Read-only checks; user grants access in Android Settings | Accessibility is clearly marked optional/advanced | 4 | Status can be stale for a moment after OEM settings return; wording must match actual feature dependencies. | Toggle every permission externally, return by Back/recents, and verify status and next action within one refresh. | lib/screens/settings_screen.dart; lib/services/native_bridge.dart; android/.../MainActivity.kt | P1 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-059 | Permissions | Just-in-time permission flow | Implemented — runtime validation pending | Usage/Overlay are requested only when Focus or Daily Limit is activated; DND only for Strict; VPN only when a browser is allowed. | HomeShell checks each prerequisite sequentially, shows a plain-language disclosure, records a pending flow, and resumes after Settings. | Feature-specific | Never required automatically; manually enabled from Advanced Protection | 5 | Repeated denial and partial grants need friction testing. | Fresh install: trigger Normal, Daily Limit, Strict, and allowed-browser flows separately; verify no unrelated prompt appears. | lib/screens/home_shell.dart; lib/screens/settings_screen.dart | P0 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-060 | Permissions | Optional notification permission | Implemented — runtime validation pending | Requests notification access for foreground-service visibility, but blocking is allowed to continue if denied. | Android 13+ runtime prompt result does not gate activation; system still exposes foreground service controls. | POST_NOTIFICATIONS (optional) | Not required | 4 | OEM behavior and user awareness differ when foreground notifications are hidden. | Deny/allow on Android 12/13/14/15/16; verify service remains alive and system disclosures are present. | lib/screens/home_shell.dart; android/.../MainActivity.kt; android/.../FocusUsageMonitorService.kt | P1 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-061 | Permissions | Optional battery optimization exemption | Implemented — runtime validation pending | Settings offers a manual battery reliability recommendation; onboarding does not request it. | Native checks PowerManager exemption and opens app-specific battery settings only after user action. | Ignore battery optimizations (optional, Settings-triggered) | Not required | 4 | Not exempt by default; aggressive OEM killers may still terminate services even when unrestricted. | Test optimized/unrestricted states and vendor auto-start/background-lock settings across OEMs. | lib/screens/settings_screen.dart; android/.../MainActivity.kt | P1 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-062 | Reliability | Foreground protection service | Implemented with platform limits | Keeps compatible Focus or daily-limit monitoring alive in the background. | Android specialUse foreground service runs package-only observation and displays an ongoing system notification/control. | FOREGROUND_SERVICE + FOREGROUND_SERVICE_SPECIAL_USE; notification optional | Stops owning Focus only while Accessibility heartbeat is healthy | 3 | Google Play special-use declaration review and OEM task killers are release risks. | Run 8h soak tests under Doze, battery saver, memory pressure, app swipe-away, screen off, and OEM auto-start disabled/enabled. | android/.../FocusUsageMonitorService.kt; android/app/src/main/AndroidManifest.xml | P0 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-063 | Reliability | Session and break timeout alarms | Implemented — runtime validation pending | Ends fixed sessions, temporary tools, and breaks even while UI is not open. | AlarmManager uses elapsed-realtime wakeups with allow-while-idle and RTC fallback for one break path; receivers sanitize and reconcile state. | No exact-alarm permission | Not required | 4 | Alarms are inexact and can be deferred; observer/reopen reconciliation is required for immediate correction. | Test Doze, reboot, force-stop/reopen, time changes, and timeout races; verify cleanup occurs once. | android/.../TrackerConfig.kt; android/.../FocusSessionTimeoutReceiver.kt; android/.../FocusBreakTimeoutReceiver.kt; android/.../StudyToolTimeoutReceiver.kt | P0 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-064 | Reliability | Monotonic timing and wall-clock recovery | Implemented — runtime validation pending | Protects active durations from manual clock changes while retaining a reboot recovery anchor. | elapsedRealtime drives same-boot duration math; wall-clock deadline is retained for reboot and Continuous-timer recovery. | None | Not required | 4 | Reboot resets elapsedRealtime; daylight/timezone/manual changes and invalid stored anchors need a device test matrix. | Move clock ±24h, change timezone, reboot, and simulate stale/corrupt preferences during every mode and break. | android/.../TrackerConfig.kt; android/.../StartupStateSanitizer.kt | P0 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-065 | Reliability | Protection restoration after reboot/update/clock change | Implemented — runtime validation pending | Reconciles active session, DND, daily limits, and compatible service after BOOT_COMPLETED, app update, TIME_SET, or TIMEZONE_CHANGED. | Manifest receiver sanitizes state, invalidates usage cache, completes expired sessions, reconciles DND, and restarts monitoring when permissions remain ready. | RECEIVE_BOOT_COMPLETED; previously granted Usage/Overlay/DND | Accessibility restarts under Android; compatible service is explicitly restarted when ready | 4 | Receiver is not direct-boot aware, so restoration begins after user unlock. VPN start is indirectly reconciled by the active monitor and must be verified. | Reboot locked/unlocked, update APK, set time/timezone, and verify Focus/limits/DND/VPN with logs. | android/.../ProtectionRestoreReceiver.kt; android/app/src/main/AndroidManifest.xml | P0 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-066 | Reliability | Startup state sanitizer and legacy migration | Implemented — runtime validation pending | Repairs wrong preference types, impossible combinations, expired transient state, and legacy private data. | TrustIssueApplication and restoration/timeout paths call StartupStateSanitizer before protection logic. | None | Not required | 4 | Only known corruptions are covered; migration must be regression-tested with real previous-version data. | Install/upgrade from each supported old build and inject malformed preference fixtures; confirm safe defaults without data loss. | android/.../TrustIssueApplication.kt; android/.../StartupStateSanitizer.kt | P0 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-067 | Accessibility | Accessibility requirement badge | Implemented — runtime validation pending | Small badge marks features that actually need optional Accessibility; Settings explains core Focus works without it. | Reusable Flutter widget is placed on Advanced Protection and locked future features. | None | Informational | 5 | Current implemented Focus modes do not require the badge because they have compatible fallback; future features must use it consistently. | Audit every toggle/card and compare its real permission dependency with badge and disclosure. | lib/widgets/accessibility_requirement_badge.dart; lib/screens/settings_screen.dart; lib/screens/blocks_screen.dart | P1 | NOT RUN — user requested no compilation | Run listed device tests; no compile/runtime validation was performed.
F-068 | Future features | YouTube Shorts blocker | UI-only — Coming soon | Blocks tab shows a locked Coming soon row only; it does not block Shorts. | No active enforcement path is connected; badge communicates future Accessibility dependency. | None today | Planned/likely required | 1 | Users may mistake a visible card for a working feature unless disabled styling/copy is unmistakable. | Tap row and confirm no setting is persisted and Coming soon message is clear. | lib/screens/blocks_screen.dart | P2 | NOT RUN — user requested no compilation | Build URL/UI-level enforcement later or keep clearly disabled.
F-069 | Future features | Instagram Reels blocker | UI-only — Coming soon | Blocks tab shows a locked Coming soon row only; it does not block Reels. | No active enforcement path is connected. | None today | Planned/likely required | 1 | Fine-grained in-app content detection is fragile and Play-policy sensitive. | Tap row and confirm no false claim of active protection. | lib/screens/blocks_screen.dart | P2 | NOT RUN — user requested no compilation | Design a policy-compliant detection approach before implementation.
F-070 | Removed features | YouTube Study Mode | Removed by product decision | Feature is intentionally absent. | Removed by user decision; browser/domain protection remains separate. | None | Not applicable |  | Old screenshots/copy must not advertise it. | Search UI, strings, settings, and navigation for active YouTube Study Mode entry points. | Current Flutter UI source | N/A | NOT RUN — user requested no compilation | Remove any residual dead strings/assets if later found.
F-071 | Removed features | Prevent uninstall | Removed by product decision | No uninstall-prevention toggle is presented or implemented. | Removed by user decision; ordinary consumer apps cannot reliably prevent uninstall without device-owner/enterprise management. | None | Not applicable |  | Strict/Locked can still be bypassed by uninstalling or force-stopping the app. | Confirm no device-admin/device-owner/uninstall interception code or UI exists. | Current Flutter/Android source | N/A | NOT RUN — user requested no compilation | Keep removed unless an enterprise device-owner edition is planned.
F-072 | Removed features | Block split screen and floating windows | Removed by product decision | No dedicated strict-protection toggles exist. | Removed by user decision; general blocking still attempts to detect foreground packages. | None | Not applicable |  | Multi-window, PiP, and floating-window edge cases remain platform limitations for current blocking. | Verify UI absence; include split-screen/PiP in core blocker testing rather than claiming dedicated prevention. | Current Flutter UI source | N/A | NOT RUN — user requested no compilation | Keep removed; document current limitation.
F-073 | Removed features | Block phone home screen | Removed by product decision | No home-screen blocking option is present. | Removed from the requested product scope; launcher remains a safe navigation surface. | None | Not applicable |  | Users can remain on launcher but cannot use blocked apps. | Confirm no UI toggle and launcher is never blocked. | Current Flutter/Android source | N/A | NOT RUN — user requested no compilation | Keep removed.
F-074 | Code health | Duplicate Flutter EmergencyExitScreen | Legacy/unreferenced — cleanup pending | No user-facing effect; the actual exit screen is native FocusGateActivity. | The Dart EmergencyExitScreen class is defined but has no active reference; native emergency exit is launched through MethodChannel. | None | Not applicable | 2 | Duplicate behavior can drift and confuse future maintenance. | Run reference search and confirm no route constructs EmergencyExitScreen; then remove after a normal build/test cycle. | lib/screens/emergency_exit_screen.dart; android/.../FocusGateActivity.kt; android/.../MainActivity.kt | P2 | NOT RUN — user requested no compilation | Remove or deliberately wire it after compile/runtime validation.

## Permission Matrix
Permission & Access Matrix
Exactly when each access is requested, why it exists, what data is used, denial behavior, and the Accessibility relationship.
Permission / access | Android type | When requested | Required? | Features | Data used | Explicitly not used | Fallback / denial | Accessibility relation | Risk / policy note | Test
Usage Access (PACKAGE_USAGE_STATS) | Special app access | Only when starting Focus or activating the first Daily App Limit | Required for compatible Focus and Daily App Limits | Foreground package detection; daily usage totals/limits | Package names and change/usage times | Screen text, passwords, messages, notifications | Feature is saved but cannot activate; user can retry later | Focus can shift to Accessibility for faster events, but Daily Limits still use Usage Access | OEM UsageStats delay; explain prominent core functionality | Grant/deny/revoke during Focus and Daily Limit; compare totals with Digital Wellbeing.
Display over other apps (SYSTEM_ALERT_WINDOW) | Special app access | Only when starting Focus or activating a Daily App Limit | Required by current core blocking design | Immediate safety overlay; floating Focus pill | No user content; draws TrustIssue UI above apps | Reading target app content | Focus/limit cannot activate | Still required even when Accessibility is enabled | OEM restrictions and secure windows; Play disclosure | Grant/revoke mid-session; verify no stuck overlay and fail-safe messaging.
POST_NOTIFICATIONS | Runtime permission on Android 13+ | After core Focus/limit access is ready | Optional | Visible foreground-service notifications | None | Reading or deleting other apps' notifications | Blocking continues; Android system still exposes active service controls | None | User may be less aware of background protection | Deny on Android 13–16 and run an 8-hour soak.
Do Not Disturb policy access (ACCESS_NOTIFICATION_POLICY) | Special policy access | Only when starting Strict or Locked Strict | Required for Strict modes by current product rule | Alarms-only DND; notification/call visual suppression | Reads and temporarily changes DND filter/policy | Notification contents | Strict does not start | None | OEM/Android-version behavior; restore pre-existing DND safely | Pre-enable user DND, run/cancel/expire/reboot Strict, verify exact restoration.
Android VPN consent (BIND_VPN_SERVICE) | System VPN consent | Only when an installed browser is allowed during Focus | Conditional | Browser hostname filtering | Allowed-browser DNS hostnames; DNS messages forwarded to Cloudflare Family | Page body, passwords, search text, browser history, TLS decryption | Browsers are moved to blocked policy (fail closed) | None | Conflicts with another VPN; external DNS provider; Play VPN declaration | Allow one browser; decline/revoke consent; verify it never opens unprotected.
Accessibility service | Special accessibility access | Never automatically; manual Advanced Protection action | Optional for all implemented core Focus modes | Faster package transition detection and stronger cross-app handoffs | TYPE_WINDOW_STATE_CHANGED package names | Accessibility node text, passwords, form values, screen contents | Usage Access compatible observer handles Focus | This is the optional engine itself | Bank/payment apps may block any enabled service; stringent Play policy | Payment/banking matrix with service off/on; kill service and confirm 10s heartbeat fallback.
Battery optimization exemption | Optional OS/vendor setting | Never in onboarding; only user-initiated from Settings | Optional but useful on aggressive OEMs | Improves survival of compatible monitor and daily limits | None | None | Features still run but may be killed/delayed | Helpful mainly for compatible foreground service; not a guarantee for either engine | Vendor-specific background/autostart controls remain | Optimized versus unrestricted 8-hour soak on top OEMs.
RECEIVE_BOOT_COMPLETED | Install-time normal permission | No user prompt | Required for reboot restoration | Restores active protection/daily limits/DND after user unlock | Local stored state only | No direct-boot data before unlock | Protection resumes when the app is next opened | Android separately manages Accessibility service restart | Receiver is directBootAware=false | Reboot and wait before/after unlock; confirm restoration timing.
INTERNET + ACCESS_NETWORK_STATE | Normal permissions | No user prompt | Only materially used by web protection | Encrypted family DNS and network health | DNS request/response and connectivity state | No TrustIssue account or analytics upload is implemented | VPN degrades and browsers should fail closed | None | Cloudflare external dependency | Offline, captive portal, TLS intercept, Wi-Fi/mobile handoff.
FOREGROUND_SERVICE + SPECIAL_USE | Manifest/service capability | No separate prompt | Required for compatible monitoring | Focus and daily limit foreground service | Package-only observations and local state | Screen content | Accessibility can handle Focus, but daily limits still need compatible monitor | Warm fallback remains available | Google Play special-use subtype review required | Android 14–16 service-start compliance and Play pre-launch checks.
FOREGROUND_SERVICE_SYSTEM_EXEMPTED | Manifest/service capability for VPN | No separate prompt | Used by VpnService declaration | Focus web protection foreground VPN | Allowed-browser DNS | TLS payload | Browsers fail closed | None | Validate target-SDK/Play eligibility for VPN systemExempted service type | Start VPN on Android 14–16 and review Play Console policy declarations.

## Test Checklist
Release Test Checklist
No test below has been executed. Fill Device/Android, evidence, and PASS/FAIL only after running the exact build on real devices.
Test ID | Area | Scenario | Preconditions | Steps | Expected result | Priority | Status | Device / Android | Evidence / notes
T-001 | Onboarding | Fresh install requests no permission | Fresh install / cleared data | Complete onboarding without opening a protected feature. | No Android permission/special-access screen appears. | P0 | NOT RUN
T-002 | Permissions | Normal Focus just-in-time flow | No access granted | Start Normal Focus and follow prompts. | Only Usage, Overlay, then optional notifications are requested. | P0 | NOT RUN
T-003 | Permissions | Strict adds only DND | Usage/Overlay granted; DND denied | Start Strict. | DND disclosure appears; Accessibility and battery are not requested. | P0 | NOT RUN
T-004 | Permissions | Allowed browser adds only VPN | Focus access ready; browser allowed | Start Focus. | VPN disclosure/consent appears; denial blocks browser and cancels unsafe start. | P0 | NOT RUN
T-005 | Compatible engine | Normal Focus without Accessibility | Accessibility OFF; Usage/Overlay ON | Start Focus; open each blocked app 20 times. | Gate appears every time with acceptable latency and no unprotected use. | P0 | NOT RUN
T-006 | Accessibility engine | Fast block with Accessibility | Accessibility ON and healthy | Start Focus; rapidly switch to blocked apps. | Single immediate gate; no duplicate compatible gate. | P0 | NOT RUN
T-007 | Hybrid engine | Heartbeat fallback | Active Focus with Accessibility ON | Disable/kill Accessibility service while switching apps. | Compatible protection takes ownership within 10s and no persistent gap occurs. | P0 | NOT RUN
T-008 | Compatibility | Payment app with Accessibility OFF | Accessibility OFF | Open representative UPI/bank/payment apps before/during Focus when allowed. | Apps do not complain about TrustIssue Accessibility; Focus behavior follows rules. | P0 | NOT RUN
T-009 | Compatibility | Payment app with Accessibility ON | Accessibility ON | Open same payment matrix. | Any third-party refusal is documented; user can disable optional Accessibility and core app continues. | P0 | NOT RUN
T-010 | Blocking UI | Gate in recents | Active Focus | Open blocked Chrome/Instagram; open recents. | TrustIssue gate is its own card; target app remains behind/in memory; no misleading force-close claim. | P0 | NOT RUN
T-011 | Blocking UI | Animation and safety overlay handoff | Compatible engine | Record blocked app launch in slow motion. | No content flash beyond accepted threshold; overlay disappears only after gate is visible. | P0 | NOT RUN
T-012 | Blocking UI | No stuck overlay | Active Focus | Rotate, lock/unlock, crash/reopen gate, end Focus. | Overlay/pill is removed from allowed apps and after session end. | P0 | NOT RUN
T-013 | Media | Blocked foreground video stops | YouTube/VLC playing | Block the playing app. | Playback becomes inaudible quickly and does not continue indefinitely behind gate. | P0 | NOT RUN
T-014 | Media | Spotify is not permanently paused | Spotify in background + another blocked media app | Trigger gate repeatedly. | Spotify may briefly duck/pause but resumes after transient focus release. | P0 | NOT RUN
T-015 | Timer | Normal timer completion | 1-minute test configuration | Run with screen on and off. | Ends exactly once, removes block UI/service state, reports duration. | P0 | NOT RUN
T-016 | Timer | Mode maximum validation | Idle | Try Normal >24h, Strict >8h, Locked >3h. | UI/native reject over-limit values; exact maximum is accepted. | P0 | NOT RUN
T-017 | Stopwatch | Count-up and normal exit | Normal Stopwatch | Use selected/unselected apps; end Focus. | Elapsed time is monotonic and stop confirmation works. | P0 | NOT RUN
T-018 | Stopwatch | Strict Stopwatch exit | Strict Stopwatch | Trigger pill/home exit. | Protected 60s/10-word emergency exit is required. | P0 | NOT RUN
T-019 | Locked Strict | Locked disabled for Stopwatch | Stopwatch selected | Open protection choices. | Locked is unavailable and cannot be persisted through restart. | P0 | NOT RUN
T-020 | Locked Strict | No early-exit path | Active Locked Strict | Try home, pill, gate, back, notification, deep link, app restart. | No emergency/end button or successful native stop path exists. | P0 | NOT RUN
T-021 | Locked Strict | Natural timeout and DND release | Short debug/test duration or boundary harness | Let session expire with screen off. | Session completes once and original DND state returns. | P0 | NOT RUN
T-022 | Strict | Preparation wait/skip/cancel | Strict configured | Exercise all three paths and background interruption. | Only wait/skip starts; cancel/interruption remains safe. | P1 | NOT RUN
T-023 | Strict | Emergency exit validation | Active Strict | Try 0, 9, 10 words before/after 60s. | Exit enabled only after both requirements; attempts/cancel/success recorded correctly. | P0 | NOT RUN
T-024 | DND | Existing user DND restored | User DND already set | Start and end Strict normally/emergency/timeout. | TrustIssue releases only its own state and restores original filter/policy. | P0 | NOT RUN
T-025 | DND | Incoming communications | Active Strict/Locked | Send call, emergency call, SMS, heads-up, alarm. | Behavior matches alarms-only promise and safety expectations on each OEM. | P0 | NOT RUN
T-026 | Breaks | Break earning boundaries | Timer and Stopwatch | Cross 30/60-minute focused thresholds. | Correct break count/budget appears once at each threshold. | P1 | NOT RUN
T-027 | Breaks | Up to three selected break apps | Break available | Select 1/3/4 apps and launch selected/unselected apps. | Maximum is enforced; only selected and safety apps open. | P0 | NOT RUN
T-028 | Breaks | Early return preserves unused budget | Active break | End after 30s; take next allowed break. | Unused time is returned exactly once and reports match. | P1 | NOT RUN
T-029 | Breaks | Expiry under Doze/reboot | Active break | Screen off/Doze/reboot across expiry. | Rules restore at alarm or first reconciliation; no stuck break. | P0 | NOT RUN
T-030 | Tracking | Continuous timer accounting | Book/Continuous mode | Spend controlled time on launcher/allowed apps and break. | Wall-clock focus excludes break and ends at expected deadline. | P1 | NOT RUN
T-031 | Tracking | Selected-app accounting | App Study | Alternate selected and unselected apps in measured intervals. | Only selected/approved tool time is credited within tolerance. | P0 | NOT RUN
T-032 | Study tools | Two-minute quick PDF | App Study + default PDF | Open PDF from selected study app; grant quick access. | Counts study, expires once, and returns to source; second grant unavailable. | P0 | NOT RUN
T-033 | Study tools | Session-long default PDF | Eligible selected PDF reader | Grant for session; reopen repeatedly. | Grant lasts only current Focus and counts time. | P1 | NOT RUN
T-034 | Study tools | Gallery confirmation false-positive control | App Study | Open Gallery directly and through study app/system picker. | Gallery never gets silent full-session access; confirmation is clear. | P0 | NOT RUN
T-035 | Study tools | PDF reader removed/changed | Configured default PDF reader | Uninstall/disable/change handler. | Start flow asks for a valid new reader and does not crash. | P1 | NOT RUN
T-036 | Daily limits | Basic enforcement | Usage/Overlay ready | Set a short limit; consume it; reopen app. | Daily-limit gate appears consistently and Focus state remains independent. | P0 | NOT RUN
T-037 | Daily limits | Midnight reset | Limit exhausted before midnight | Cross local midnight and time zone. | New day's usage resets without corrupting previous report. | P0 | NOT RUN
T-038 | Daily limits | All-day survival | Limit active; no Focus | 8–24h soak with app swipe-away, screen off, battery saver. | Monitor survives or restores; notification/system disclosure remains correct. | P0 | NOT RUN
T-039 | Web | All browsers blocked means no VPN | Blocklist includes all browsers | Start Focus. | VPN does not start and browsers remain blocked. | P1 | NOT RUN
T-040 | Web | Adult and SafeSearch filtering | Allowed browser + VPN | Visit curated adult and supported search/video hosts. | Adult domains fail; SafeSearch aliases behave as designed. | P0 | NOT RUN
T-041 | Web | Blocked app web mapping | Known app blocked; browser allowed | Visit mapped canonical/alternate domains. | Mapped domains block with app+web category; gaps are documented. | P1 | NOT RUN
T-042 | Web | Custom domains | VPN active | Add exact domain; test root/subdomain/non-match. | Root/subdomain block; unrelated suffix does not. | P1 | NOT RUN
T-043 | Web | Secure DNS/bypass attempts | VPN active | Enable browser Secure DNS/Private DNS; test proxy/DoH endpoints. | Known bypasses block; any unknown bypass is documented as a limitation. | P0 | NOT RUN
T-044 | Web | VPN consent revoked/failure | Active Focus with browser | Revoke VPN, kill service, break upstream DNS. | State becomes reconnecting/degraded and browser fails closed. | P0 | NOT RUN
T-045 | Web | Network transitions | VPN active | Wi-Fi↔mobile, offline, captive portal, IPv4/IPv6. | Protection recovers without leaking unfiltered browser DNS. | P0 | NOT RUN
T-046 | Reports | Controlled metric reconciliation | Known scripted sessions | Generate starts/completions/attempts/returns/exits/breaks. | Daily, 7-day, 30-day and per-app values equal independent calculation. | P0 | NOT RUN
T-047 | Reports | Clear local reports | History present | Clear in Settings; restart. | History is empty, configuration and active protection remain intact. | P1 | NOT RUN
T-048 | Diagnostics | Log privacy | All features exercised | Export log and inspect. | No screen text, password, message, notification body, typed emergency reason, or full URL is present. | P0 | NOT RUN
T-049 | Recovery | Reboot restore | Active Focus/Strict/limit | Reboot, wait at lock screen, unlock. | Expired sessions finish; DND/monitor restore safely after unlock. | P0 | NOT RUN
T-050 | Recovery | App update restore | Active modes | Install update over app. | State sanitizer runs; protection and DND are coherent. | P0 | NOT RUN
T-051 | Recovery | Manual clock/timezone changes | Active timer/break/limit | Move time ±24h and change zone. | Monotonic active duration is not extended/bypassed; daily boundary behavior is defined. | P0 | NOT RUN
T-052 | Permissions | Revoke Usage or Overlay mid-session | Active Focus | Revoke each from Settings. | App surfaces degraded/not-ready state and does not claim protection it cannot provide. | P0 | NOT RUN
T-053 | Permissions | DND revoked mid-Strict | Active Strict | Revoke policy access. | State is reconciled safely; user receives clear warning; cleanup does not alter unrelated DND. | P0 | NOT RUN
T-054 | UI | Large text/small screen/accessibility semantics | Various display settings | Use 2x font, TalkBack, 320dp width, landscape. | Core actions remain visible, labeled, and operable. | P1 | NOT RUN
T-055 | Platform | Split screen/PiP/floating windows | Active Focus | Open blocked apps through each mode. | Current behavior is measured; unsupported gaps are documented, not advertised as protected. | P0 | NOT RUN
T-056 | Platform | Rapid app/recents/notification switching | Active Focus | 100 rapid transitions and deep links. | No crash, duplicate gates, or meaningful unprotected window. | P0 | NOT RUN
T-057 | OEM | Battery optimization matrix | Pixel/Samsung/Xiaomi/Oppo/Vivo/OnePlus | Optimized/unrestricted 8h soak. | Survival rate and required vendor guidance are documented. | P0 | NOT RUN
T-058 | Android versions | Android 10–16 compatibility | Representative devices/emulators | Run start/block/end, FGS, DND, VPN, reboot suite. | No OS-specific crash or policy violation; differences are documented. | P0 | NOT RUN
T-059 | Store policy | Google Play declaration review | Release candidate | Review Usage Access, overlay, Accessibility, VPN, and specialUse forms/disclosures. | Declarations match actual source/data use and user-facing disclosures. | P0 | NOT RUN
T-060 | Performance | CPU/battery/memory profile | Compatible and Accessibility engines | 8h profile idle/active and 300+ apps. | Polling, icon cache, VPN, and reports stay within agreed budgets; no leaks. | P0 | NOT RUN

## Pending & Removed
Pending, Limited, Coming-soon & Removed
This separates unfinished validation from deliberate product removal and unavoidable Android limitations.
Item ID | Topic | Classification | Current truth | Best next action | Priority
P-001 | Build validation | Pending | No Flutter/Android compile was run because the user explicitly requested no compilation. | Run formatter/analyzer/build in a later approved session. | P0
P-002 | Runtime validation | Pending | All implemented features are source-reviewed only; none are marked device-verified. | Execute Test Checklist and record device/build/evidence. | P0
P-003 | OEM reliability | Pending | Compatible polling, overlays, service survival, and DND vary substantially by vendor. | Complete Pixel/Samsung/Xiaomi/Oppo/Vivo/OnePlus matrix. | P0
P-004 | Payment-app friction | Known platform issue | Some bank/payment apps reject any enabled Accessibility service even if TrustIssue reads only package changes. | Keep Accessibility optional, explain benefit/tradeoff, and test top payment apps per market. | P0
P-005 | Play policy | Pending | Accessibility, Usage Access, overlays, VPN, and specialUse foreground service require accurate declarations and prominent disclosures. | Legal/policy review before release; preserve package-only/no-content behavior. | P0
P-006 | Locked Strict safety | High-risk validation | No-exit behavior has high impact if timeout, reboot, or DND cleanup fails. | Dedicated destructive/soak test plan and recovery review before public enablement. | P0
P-007 | Web coverage | Platform limitation | DNS-only VPN cannot guarantee blocking of every encrypted DNS/proxy/IP/path-level bypass. | Publish honest scope; expand maintained rule lists and add bypass regression corpus. | P0
P-008 | Web external dependency | Pending | Cloudflare Family availability and policy affect allowed browser DNS. | Document provider, privacy, outage behavior, and consider configurable/provider redundancy. | P1
P-009 | Daily-limit precision | Pending | UsageStats aggregation and midnight behavior need device evidence. | Reconcile with Digital Wellbeing across Android/OEM/timezone matrix. | P0
P-010 | Study-tool handoff | Platform limitation | Without Accessibility, Android cannot always distinguish direct Gallery/PDF opening from a study-app handoff. | Retain small confirmation gate; tune heuristics with false-positive telemetry only if privacy-safe. | P1
P-011 | Media ownership | Platform limitation | AudioManager.isMusicActive is global, so transient focus may briefly affect unrelated music. | Test market-leading players; keep no-media-key design; consider user setting if complaints persist. | P1
P-012 | Multi-window/PiP | Known gap | Dedicated split-screen/floating-window prevention was removed, but these modes can challenge foreground detection. | Measure and document current coverage; do not market full prevention. | P0
P-013 | Shorts blocker | Coming soon | UI-only; no enforcement. | Keep locked badge or remove card until an approved implementation exists. | P2
P-014 | Reels blocker | Coming soon | UI-only; no enforcement. | Keep locked badge or remove card until an approved implementation exists. | P2
P-015 | Dead code | Cleanup pending | Flutter EmergencyExitScreen duplicates native flow and appears unreferenced. | Remove after build/reference/runtime validation. | P2
P-016 | Copy consistency | Review pending | Settings privacy copy and current gate/Home behavior must describe the actual implementation exactly. | Run source-to-copy privacy review; avoid saying force-close. | P1
P-017 | Diagnostics privacy | Review pending | Package/domain metadata can be sensitive even without content. | Set retention/size limits, redact where possible, and verify export fixtures. | P0
P-018 | Removed: YouTube Study | Removed | Removed by product decision. | Keep removed and clean residual copy/assets if found. | N/A
P-019 | Removed: Prevent uninstall | Removed | Not requested and not reliable for a normal consumer app. | Only reconsider for device-owner enterprise edition. | N/A
P-020 | Removed: split/floating/home block | Removed | Removed by product decision. | Document limitations and keep UI absent. | N/A

## Architecture
Protection Architecture
The important ownership and fallback relationships behind Focus, limits, web protection, study handoffs, and restoration.
Component | Responsibility | Interface / trigger | Reliability / fallback | Primary source
Flutter UI / HomeShell | Configuration, tabs, just-in-time disclosures, start/stop orchestration | MethodChannel to native Android | Persists inactive config before native activation; restores config on failure | lib/screens/home_shell.dart
SettingsStore | Local Focus policy/session/limits/domain persistence and normalization | SharedPreferences | Clamps mode durations and disallows Locked Stopwatch | lib/services/settings_store.dart
MainActivity bridge | Permission checks/settings intents, app discovery/icons, native session commands | Flutter MethodChannel | Returns structured success/message maps | android/.../MainActivity.kt
TrackerConfig | Authoritative native session state, timing, breaks, analytics, alarms | SharedPreferences + AlarmManager | Monotonic timing, wall recovery, finish-if-expired reconciliation | android/.../TrackerConfig.kt
FocusPolicyEngine | Pure allow/block decision from snapshot and safety flags | Called by both observers | Same policy across compatible/Accessibility engines | android/.../FocusPolicyEngine.kt
Accessibility observer | Fast TYPE_WINDOW_STATE_CHANGED package events | Starts native gates/pill; 3s heartbeat | Compatible service remains warm and takes over if heartbeat stale | android/.../SelfControlAccessibilityService.kt
Compatible observer | UsageStats polling for Focus and daily limits | 300ms active loop; foreground service | Safety overlay before Activity; retains daily-limit ownership | android/.../FocusUsageMonitorService.kt
ProtectionAccess | Permission readiness and observer ownership | Usage/Overlay checks + Accessibility heartbeat | 10s stale threshold prevents enabled-but-dead service gap | android/.../ProtectionAccess.kt
FocusBlockOverlayController | Immediate minimal opaque gate while Activity starts | SYSTEM_ALERT_WINDOW | Hidden on ACTION_GATE_VISIBLE; OEM fallback if Activity is delayed | android/.../FocusBlockOverlayController.kt
FocusGateActivity | Primary blocked/daily-limit/break/exit UI and live timer | Native singleTask Activity | Dismisses when session no longer applies; mode-specific exit controls | android/.../FocusGateActivity.kt
FocusPillController | Draggable overlay timer and quick controls | WindowManager overlay | Auto-hide/collapse, saved position, visibility policy | android/.../FocusPillController.kt
BlockedMediaController | Stops lingering blocked-app audio without global media keys | Transient AudioFocus | 350ms settle then 850ms focus hold/release | android/.../BlockedMediaController.kt
UsageStatsReader | Today's app usage and latest foreground package | UsageStatsManager | 2.5s usage-total cache with invalidation | android/.../UsageStatsReader.kt
WebProtectionConfig | Browser discovery, domain rules, VPN state/coverage | PackageManager + local preferences | Fail-closed status and 15s browser cache | android/.../WebProtectionConfig.kt
FocusWebProtectionService | Allowed-browser split VPN and DNS policy | VpnService + Cloudflare Family DoH | Health probes, 6s reconnect grace, 30s DNS cache, degraded fail-closed state | android/.../FocusWebProtectionService.kt
StudyToolResolver/Gate | PDF/Gallery classification and explicit temporary/session grants | Package/intent queries + native Activity | Once-per-tool quick grant and timeout/return path | android/.../StudyToolResolver.kt; android/.../StudyToolGateActivity.kt
StrictFocusDndController | Apply/release only TrustIssue-owned alarms-only DND | NotificationManager policy access | Saves previous state and reconciles after lifecycle events | android/.../StrictFocusDndController.kt
Restore receivers/sanitizer | Reboot/update/time/timeout restoration | BroadcastReceiver + application startup | Repairs types, expires stale state, restarts compatible monitor | android/.../ProtectionRestoreReceiver.kt; android/.../StartupStateSanitizer.kt
Reports | Local summaries, charts, outcomes, break and app metrics | Native daily JSON → Flutter aggregation | No cloud dependency; clear/export controls | lib/screens/analytics_screen.dart; android/.../TrackerConfig.kt

## How to Read
How to use this workbook
A feature can be source-complete and still be unsafe to call reliable until its test rows pass on real target devices.
Step | Where | What to do
1 | Start at Executive Summary | Read the bottom line and remember the audit did not compile or run the app.
2 | Filter Feature Inventory | Use Implementation status + Release priority. P0 means release-blocking validation.
3 | Read reliability correctly | A 4/5 means the design is strong but not verified. A 3/5 often reflects Android/OEM limits, not necessarily poor code.
4 | Use Permission Matrix for onboarding | It is the source of truth for just-in-time prompts and for explaining Accessibility is optional.
5 | Execute Test Checklist | Change Status only to PASS/FAIL/BLOCKED and attach device/build/video/log evidence.
6 | Do not market beyond evidence | Do not say force-close, impossible to bypass, all websites blocked, or payment apps compatible until supported by tests.
7 | Release gate | All P0 tests, Play policy checks, Locked Strict safety tests, and OEM soak tests should pass before production.